Action lists

RC = Regional Coordinator

RDC = River Data Catalog

RSL = River Station List

Subtask S2.5.1

No.	Action	Responsible	Date Due	Status
1	Create & distribute regional ECOOP River Data Catalogs (RDC) V0	met.no	30.09.07	Closed
2	Find a “partner” to liaise with MOON / MED-GOOS	met.no	15.10.07	Open
3	Contact GRDC about data available (NRT and archive) and avenues for collaboration	met.no	15.10.07	Open
4	Identify and confirm national contact points in each region.	RC's	31.10.07	Closed
5	Formulate and send request for relevant information to national contact points	RC's	31.10.07	Closed
5a	Formulate and send request for relevant information to national contact points: NOOS, MED	RIKZ, met.no	31.03.07	Open
6	Criteria for selecting stations for the optimal list and the initial NRT list	met.no	30.11.07	Closed
7	Follow up requests to nat. contacts; contact nat. data providers directly as needed	RC's	15.11.07	Closed
7a	Follow up requests to nat. contacts: NOOS, MED	RIKZ, met.no	30.04.08	Open
8	Revise regional RDC V0 based on info from nat. contacts (draft ECOOP RDC V1)	RC's	20.12.07	Closed
8a	Revise regional RDC V0 based on info from nat. contacts: NOOS, MED	RIKZ, met.no	30.04.08	Open
9	Draft River Station Lists (RSLs) V0.2, collated from regional RDC's	met.no	20.12.07	Closed
10	Check RDC V1 entries for consistency and completeness	AZTI,SMHI,MHI	29.02.08	Open
11	Investigate WISE as source of information / data	met.no	29.02.08	Open
12	Build regional ECOOP RSLs V0.5 from draft V0.2 and RDCs	RC's	29.02.08	Open
13	Verify RDCs V1 with nat. contacts	RC's	31.03.08	Open
14	Verify draft RSL V0.5 with nat. contacts	RC's	31.03.08	Open
15	Regional ECOOP RDCs V1, final	RC's	31.05.08	Open
16	D2.5.1.1 Regional ECOOP RDCs V1 (final)	met.no	31.05.08	Open
17	Regional ECOOP RSLs V1, final	RC's	31.05.08	Open
18	V1 list of initial NRT river stations for use in the EDMS	RC's	31.03.08	Open
19	D2.5.2.1 Regional ECOOP RSLs V1 (final)	met.no	31.08.08	Open

Subtask S2.5.2

No.	Action	Responsible	Date Due	Status
1	Propose candidate data formats	BSH	31.03.08	Closed
2	Obtain recommended procedures for providing data to EDMS	BSH	15.04.08	Closed
3	Finalize data format	met.no	15.04.08	Closed
4	ftp boxes (1 per region) established	RC's	30.04.08	Open
5	Test initial feed of NRT data from providers to ftp boxes	RC's	30.06.08	Open
6	Draft D2.5.2.2 Report on interfacing river runoff data to the EDMS offered for comment	met.no	30.05.08	Open
7	Verify access from EDMS to ftp boxes	met.no	30.05.08	Open
8	D2.5.2.2 Final	met.no	31.07.08	Open
9	Draft D2.2.4.2 appendix on river data formatting ready	met.no	30.11.08	Closed

Subtask S2.5.3

No.	Action	Responsible	Date Due	Status
1	..........	NN	??	Open
X	D2.5.3.1 Description and assessment of the ECOOP river runoff data provision	met.no	31.01.10	Open