Action lists

Subtask 2.5.1

No	Action	Resp	Due	Status
1	Create & distribute regional ECOOP River Data Catalogs V0	met.no	30.09.07	Closed
2	Find a “partner” to liaise with MOON	met.no	15.10.07	Open
3	Contact GRDC about data available (NRT and archive) and avenues for collaboration	met.no	15.10.07	Open
4	Identify and confirm national contact points in each region.	RC's	31.10.07	Open
5	Formulate and send request for relevant information to national contact points	RC's	31.10.07	Open
6	Criteria for selecting stations for the optimal list and the initial NRT list	met.no	30.09.07	Open
7	Follow up requests to nat. contacts; contact nat. data providers directly as needed	RC's	30.09.07	Open
8	Revise regional RDC V0 based on info from nat. contacts (draft ECOOP RDC V1)	RC's	15.12.07	Open
9	Submit draft RDC V1 to nat. contacts for verification	RC's	31.12.07	Open
10	Revise regional RDC's based on info from nat. contacts (ECOOP RDCs V1)	met.no	30.09.07	Open