Action lists

Subtask 2.5.1

No	Action	Resp	Due	Status
1	Create & distribute regional ECOOP River Data Catalogs V0	met.no	30.09.07	Closed
2	Find a “partner” to liaise with MOON	met.no	15.10.07	Open
3	Contact GRDC about data available (NRT and archive) and avenues for collaboration	met.no	15.10.07	Open
4	Identify and confirm national contact points in each region.	RC's	31.10.07	Open
5	Formulate and send request for relevant information to national contact points	RC's	31.10.07	Open
6	Criteria for selecting stations for the optimal list and the initial NRT list	met.no	30.09.07	Open
7	Follow up requests to nat. contacts; contact nat. data providers directly as needed	RC's	30.09.07	Open
8	Revise regional RDC V0 based on info from nat. contacts (draft ECOOP RDC V1)	RC's	15.12.07	Open
9	Submit draft RDC V1 to nat. contacts for verification	RC's	31.12.07	Open
10	Regional ECOOP River Data Catalogs V1, final version (D2.5.1.1)	met.no	31.01.08	Open
11	Draft River Station Lists for European coast, collated from regional RDC's	met.no	15.12.07	Open
11	River Station Lists for European coast V1 (D2.5.1.2)	met.no	31.01.08	Open