Action lists

Subtask 2.5.1

No	Action	Resp	Due	Status
1	Create & distribute regional ECOOP River Data Catalogs V0	met.no	30.09.07	Closed
2	Find a “partner” to liaise with MOON	met.no	15.10.07	Open
3	Contact GRDC about data available (NRT and archive) and avenues for collaboration	met.no	15.10.07	Open
4	Identify and confirm national contact points in each region.	RC's	31.10.07	Open
5	Formulate and send request for relevant information to national contact points	RC's	31.10.07	Open
6	Criteria for selecting stations for the optimal list and the initial NRT list	met.no	30.09.07	Open
7	Follow up requests to nat. contacts; contact nat. data providers directly as needed	RC's	30.09.07	Open
8	Revise regional RDC V0 based on info from nat. contacts (draft ECOOP RDC V1)	RC's	15.12.07	Open
9	Draft River Station List for European coast, collated from regional RDC's	met.no	15.12.07	Open
10	Submit draft RDC V1 to nat. contacts for verification	RC's	31.12.07	Open
11	Regional ECOOP River Data Catalogs V1, final draft	RC's	15.01.08	Open
12	River Station List for European coast V1, final draft	met.no	15.01.08	Open
13	D2.5.1.1 Regional ECOOP River Data Catalogs V1	met.no	31.01.08	Open
14	D2.5.1.2 River Station List for European coast V1	met.no	31.01.08	Open