Action lists

RC = Regional Coordinator

Subtask S2.5.1

No.	Action	Responsible	Date Due	Status
1	Create & distribute regional ECOOP River Data Catalogs V0	met.no	30.09.07	Closed
2	Find a “partner” to liaise with MOON / MED-GOOS	met.no	15.10.07	Open
3	Contact GRDC about data available (NRT and archive) and avenues for collaboration	met.no	15.10.07	Open
4	Identify and confirm national contact points in each region.	RC's	31.10.07	Closed
5	Formulate and send request for relevant information to national contact points	RC's	31.10.07	Closed
5a	Formulate and send request for relevant information to national contact points: NOOS, MED	RIKZ, met.no	31.03.07	Open
6	Criteria for selecting stations for the optimal list and the initial NRT list	met.no	30.11.07	Closed
7	Follow up requests to nat. contacts; contact nat. data providers directly as needed	RC's	15.11.07	Closed
7a	Follow up requests to nat. contacts: NOOS, MED	RIKZ, met.no	30.04.08	Open
8	Revise regional RDC V0 based on info from nat. contacts (draft ECOOP RDC V1)	RC's	20.12.07	Closed
8a	Revise regional RDC V0 based on info from nat. contacts: NOOS, MED	RIKZ, met.no	30.04.08	Open
9	Draft River Station List for European coast, collated from regional RDC's	met.no	20.12.07	Closed
10	Submit draft RDC V1 to nat. contacts for verification: BOOS, IBI, BS	AZTI,SMHI,MHI	15.03.08	Open
11	Regional ECOOP River Data Catalogs V1, final draft	RC's	31.03.08	Open
12	Regional ECOOP River Station Lists V0	RC's	31.03.08	Open
13	River Station List for European coast V1, final draft	met.no	31.05.08	Open
14	V0 (draft) list of initial NRT river stations for use in the EDMS	met.no	15.03.08	Open
15	D2.5.1.1 Regional ECOOP River Data Catalogs V1	met.no	31.05.08	Open
16	D2.5.2.1 River Station List for European coast V1	met.no	31.08.08	Open
17	V1 list of initial NRT river stations for use in the EDMS	met.no	31.01.08	Open
18	Investigate WISE as source of information / data	met.no	29.02.08	Open

Subtask S2.5.2

No.	Action	Responsible	Date Due	Status
1	..........	NN	??	Open
X	D2.5.2.1 Report on interfacing river runoff data to the EDMS	met.no	31.07.08	Open

Subtask S2.5.3

No.	Action	Responsible	Date Due	Status
1	..........	NN	??	Open
X	D2.5.3.1 Description and assessment of the ECOOP river runoff data provision	met.no	31.01.10	Open