# Subtask 2.5.2
Title: Interfacing to ECOOP Data Management System
Lead partner: met.no
Participants: All
Period: Months 4-24
⇒ Action list
## Documents and links
### Reference
- GRDC proposed format for NRT discharge data
- GRDC proposed format for NRT discharge data - earlier version
- Link to the above documents at GRDC/GTN-R
### Deliverable reports
D2.2.4.2 Data interfaces for the EDMS, v0.61 Contains description of ODV data formatting for river discharge data.
## Files
### Data files
Sample ODV file for river data (One week of daily discharge data from a Norwegian station.)
### Other files
### Activity Reports
- S2.5.1 Year1 rev 27.01.2008
- S2.5.2 Year1 rev 27.01.2008
- S2.5.3 Year1 rev 27.01.2008
- T2.5 Year1 rev 27.01.2008
## Activity description (Annex I 6.1)
S2.5.2: Interfacing to ECOOP Data Management system
Objectives: Define and test procedures for acquiring river runoff data from providers and making them available through the ECOOP data management systems.
Description: This subtask must: 1) clarify data policy issues within the various regions; 2) define data transfer procedures from data providers to the EDMS; 3) comply with data formats and procedures defined for the ECOOP Data Management system; 4) accommodate specific data exchange requirements in the regional associations; 5) test the data flow procedures on representative sources in each region. This subtask will co-ordinate closely with WP2.1 (EDMS). It will also take into account relevant European marine data management experience, such as MERSEA, SeaDataNet.
## Work Package description (Annex I 8.1)
clarify data policy issues within the various regions;
define data transfer procedures from data providers to the EDMS;
adopt data formats and procedures defined for the EDMS;
clarify data exchange requirements in the regional associations;
initial tests of the data flow procedures on representative sources in each region.
## Deliverables
No.	Title	Resp	MM	Nature	Diss	Due
D2.5.2.1*	ECOOP River Station Lists (five regional) as digital spreadsheets	met.no	9	O	PP	12
D2.5.3.1#	Interfacing river runoff data to the ECOOP Data Management System	met.no	3	R	PP	18
D2.2.4.2##	Data interfaces for the ECOOP Data Management System	CMRC	?	R	PP	18

* This deliverable was misnumbered in the DoW. It really belongs to S2.5.1. However, it's easier to leave it with the wrong number. See ECOOP Subtask S2.5.1
# This deliverable was misnumbered in the DoW. It really belongs to S2.5.2. However, it's easier to leave it with the wrong number. Summer 2008: The report has been merged into D2.2.4.2.
## There is an appendix in this report containing a description of the specific interfacing for river discharge data.