Subtask 2.5.2

Title: Interfacing to ECOOP Data Management System

Lead partner: met.no

Participants: All

Period: Months 4-24

⇒ Action list

Documents and links

Reference

GRDC proposed format for NRT discharge data

GRDC proposed format for NRT discharge data - earlier version

Link to the above documents at GRDC/GTN-R

Deliverable reports

D2.2.4.2 Data interfaces for the EDMS, v0.61 Contains description of ODV data formatting for river discharge data.

Files

Data files

Sample ODV file for river data (One week of daily discharge data from a Norwegian station.)

Other files

Activity Reports

S2.5.1 Year1 rev 27.01.2008

S2.5.2 Year1 rev 27.01.2008

S2.5.3 Year1 rev 27.01.2008

T2.5 Year1 rev 27.01.2008

Activity description (Annex I 6.1)

S2.5.2: Interfacing to ECOOP Data Management system

Objectives: Define and test procedures for acquiring river runoff data from providers and making them available through the ECOOP data management systems.

Description: This subtask must: 1) clarify data policy issues within the various regions; 2) define data transfer procedures from data providers to the EDMS; 3) comply with data formats and procedures defined for the ECOOP Data Management system; 4) accommodate specific data exchange requirements in the regional associations; 5) test the data flow procedures on representative sources in each region. This subtask will co-ordinate closely with WP2.1 (EDMS). It will also take into account relevant European marine data management experience, such as MERSEA, SeaDataNet.

Work Package description (Annex I 8.1)

clarify data policy issues within the various regions;

define data transfer procedures from data providers to the EDMS;

adopt data formats and procedures defined for the EDMS;

clarify data exchange requirements in the regional associations;

initial tests of the data flow procedures on representative sources in each region.

Deliverables

No.	Title	Resp	MM	Nature	Diss	Due
D2.5.2.1*	ECOOP River Station Lists (five regional) as digital spreadsheets	met.no	9	O	PP	12
D2.5.3.1#	Interfacing river runoff data to the ECOOP Data Management System	met.no	3	R	PP	18
D2.2.4.2##	Data interfaces for the ECOOP Data Management System	CMRC	?	R	PP	18

* This deliverable was misnumbered in the DoW. It really belongs to S2.5.1. However, it's easier to leave it with the wrong number. See ECOOP Subtask S2.5.1

# This deliverable was misnumbered in the DoW. It really belongs to S2.5.2. However, it's easier to leave it with the wrong number. Summer 2008: The report has been merged into D2.2.4.2.

## There is an appendix in this report containing a description of the specific interfacing for river discharge data.