Subtask 2.5.2

Title: Interfacing to ECOOP Data Management System

Lead partner: met.no

Participants: All

Period: Months 4-24

⇒ Action list

Documents and links

Reference

Deliverable reports

Activity description (Annex I 6.1)

S2.5.2: Interfacing to ECOOP Data Management system

Objectives: Define and test procedures for acquiring river runoff data from providers and making them available through the ECOOP data management systems.

Description: This subtask must: 1) clarify data policy issues within the various regions; 2) define data transfer procedures from data providers to the EDMS; 3) comply with data formats and procedures defined for the ECOOP Data Management system; 4) accommodate specific data exchange requirements in the regional associations; 5) test the data flow procedures on representative sources in each region. This subtask will co-ordinate closely with WP2.1 (EDMS). It will also take into account relevant European marine data management experience, such as MERSEA, SeaDataNet.

Work Package description (Annex I 8.1)

clarify data policy issues within the various regions;

define data transfer procedures from data providers to the EDMS;

adopt data formats and procedures defined for the EDMS;

clarify data exchange requirements in the regional associations;

initial tests of the data flow procedures on representative sources in each region.

Deliverables

No.	Title	Resp	MM	Nature	Diss	Due
D2.5.2.1	Interfacing river runoff data to the ECOOP Data Management System	met.no	3	R	PP	18